## Executive View
iPawcus Project Timeline - Updated View
As of September 21, 2026 ¦ Consolidated from two located workbook sources
TASKS FOUND |  |  | HISTORY WINDOW |  |  |  | LATEST PLANNED END |  |  |  | SOURCE FILES
Formula-driven monthly overview of the historical plan
Task |  | Phase |  | Start | End | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01
Color key
Requirements | Design Phase |  | System Dev 1 |  | System Dev 2 |  | System Dev 3 |  | System Dev 4 |  | Testing
Important: the source workbooks contain planned task timing but no verified completion dates or progress percentages. 'Plan elapsed' means the planned end date is before the as-of date; it does not mean the task was completed.

## Updated Gantt
iPawcus - Consolidated Gantt History
Compiled from all located Gantt workbooks ¦ Updated through September 21, 2026 ¦ Bars show planned timing, not verified completion
As of | 2026-09-21 | History start |  | Latest planned end |  | Tasks |  | Sources | 2
[9 empty] | 2026-01-05 |  |  |  | 2026-02-02 |  |  |  | 2026-03-02 |  |  |  |  | 2026-04-06 |  |  |  | 2026-05-04 |  |  |  | 2026-06-01 |  |  |  |  | 2026-07-06 |  |  |  | 2026-08-03 |  |  |  |  | 2026-09-07
ID | Phase | Task | Planned Start | Planned End | Source Period | Schedule State | Reported Status | Notes | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28

## History
ID | Phase | Task | Planned Start | Planned End | Duration (days) | Original Period Label | Source Workbook | Source Sheet | Source Cell/Span | Date Basis | Increment | Reported Status | Notes
1 | Requirements | Interview with Vetfocus Clinic & identify system modules | 2026-01-01 | 2026-03-31 |  | January-March 2026 | saving one gantt.xlsx | Sheet1 | F11:G12 | Month range stated in source header | Preparation | Not documented | Spelling normalized from the source workbook.
2 | Requirements | Identify system modules | 2026-04-01 | 2026-04-10 |  | April 1-10, 2026 | saving one gantt.xlsx | Sheet1 | I11:R12 | Exact dates stated in source | Increment 1 | Not documented
3 | Requirements | Identify system modules - follow-up | 2026-05-18 | 2026-05-23 |  | May 2026 | saving one gantt.xlsx | Sheet1 | AN11:AQ12 | Approximate dates inferred from bar position | Increment 2 | Not documented | Use the original source if exact May dates become available.
4 | Design Phase | Design user access | 2026-04-16 | 2026-04-23 |  | April 2026 | saving one gantt.xlsx | Sheet1 | S13:W14 | Approximate dates inferred from bar position | Increment 1 | Not documented
5 | Design Phase | Design role management | 2026-05-20 | 2026-05-27 |  | May 2026 | saving one gantt.xlsx | Sheet1 | AP13:AT14 | Approximate dates inferred from bar position | Increment 2 | Not documented
6 | System Dev 1 | Landing page development | 2026-04-24 | 2026-04-30 |  | April 2026 | saving one gantt.xlsx | Sheet1 | X16:AB17 | Approximate dates inferred from bar position | Increment 1 | Not documented
7 | System Dev 1 | User profiles | 2026-05-25 | 2026-05-31 |  | May 2026 | saving one gantt.xlsx | Sheet1 | AS16:AW17 | Approximate dates inferred from bar position | Increment 2 | Not documented
8 | System Dev 2 | Register and login page | 2026-04-28 | 2026-05-03 |  | April-May 2026 | saving one gantt.xlsx | Sheet1 | AA18:AD19 | Approximate dates inferred from bar position | Increment 1 | Not documented
9 | System Dev 2 | Accounts management module | 2026-05-29 | 2026-06-08 |  | May-June 2026 | saving one gantt.xlsx | Sheet1 | AV18:BB19 | Approximate dates inferred from bar position | Increment 2 | Not documented
10 | System Dev 3 | User registration | 2026-05-02 | 2026-05-09 |  | May 2026 | saving one gantt.xlsx | Sheet1 | AD20:AH21 | Approximate dates inferred from bar position | Increment 1 | Not documented | The adjacent 2031 placeholder date was ignored because the task bar is under May 2026.
11 | System Dev 3 | Role-based logic control | 2026-06-04 | 2026-06-14 |  | May-June 2026 | saving one gantt.xlsx | Sheet1 | AZ20:BF21 | Approximate dates inferred from bar position | Increment 2 | Not documented | The adjacent 2031 placeholder date was ignored.
12 | System Dev 4 | Admin and veterinarian account creation page | 2026-05-07 | 2026-05-15 |  | May 2026 | saving one gantt.xlsx | Sheet1 | AG22:AL23 | Approximate dates inferred from bar position | Increment 1 | Not documented | The adjacent 2032 placeholder date was ignored.
13 | System Dev 4 | Clinic account monitoring module | 2026-06-09 | 2026-06-14 |  | June 2026 | saving one gantt.xlsx | Sheet1 | BC22:BF23 | Approximate dates inferred from bar position | Increment 2 | Not documented | The adjacent 2032 placeholder date was ignored.
14 | Testing | Testing - round 1 | 2026-05-10 | 2026-05-12 |  | May 2026 | saving one gantt.xlsx | Sheet1 | AI24:AJ25 | Approximate dates inferred from bar position | Increment 1 | Not documented | The adjacent 2033 placeholder date was ignored.
15 | Testing | Testing - round 2 | 2026-06-09 | 2026-06-11 |  | June 2026 | saving one gantt.xlsx | Sheet1 | BC24:BD25 | Approximate dates inferred from bar position | Increment 2 | Not documented | The adjacent 2033 placeholder date was ignored.

## Sources
Source Workbook Reconciliation
Source | Original Path | Last Modified | Role | Content Used | Notes
saving one gantt.xlsx | D:\CAPSTONE _101\saving one gantt.xlsx | 2026-03-24 21:48 | Historical task source | 15 planned task bars across requirements, design, development, and testing | Task text and merged-bar placement were consolidated. Obvious 2031-2033 placeholder labels were not treated as real dates.
gantt-chart-template.xlsx | D:\CAPSTONE _101\gantt-chart-template.xlsx | 2026-09-21 12:50 | Layout/reference template | Formula-driven weekly Gantt pattern and example structure | The example tasks dated 2024 were excluded because they are generic template content.
Date reconstruction rules
1. Exact dates were retained where the source explicitly stated them.
2. Month-only task bars were converted to approximate dates based on their position within the source month band.
3. The original period label and source cell span are retained in History so every approximation is auditable.
4. No completion status was inferred. Reported Status defaults to 'Not documented'.
5. The red-tinted week in Updated Gantt marks the week containing September 21, 2026.