## Sheet1
Gantt Chart
iPawcus
| January - March | 2026-04-01 | [19 empty] | 2026-05-01 | [19 empty] | 2026-06-01 | [19 empty] | 2026-07-01 | [19 empty] | 2026-08-01 | [19 empty] | 2026-09-01 | [19 empty] | 2026-10-01 | [19 empty] | 2026-11-01
Incremental Methodology |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27 |  |  |  |  | Week 28 |  |  |  |  | Week 29 |  |  |  |  | Week 30 |  |  |  |  | Week 31 |  |  |  |  | Week 32
|  | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5 | D1 | D2 | D3 | D4 | D5
Increments | [11 empty] | INCREMENT 1 | [19 empty] | Week 7 D1: INCREMENT 2
Requirements | Interview with Vetfocus Clinic & Indentifying System Modules | April 1-10, 2026 | [29 empty] | Week 7 D1: May, 2026
|  | Indentifying System Modules | [29 empty] | Week 7 D1: Identifying System Modules
Design Phase | [11 empty] | April, 2026 | [19 empty] | Week 7 D3: May, 2026
|  | Indentifying System Modules | [9 empty] | Designing User Access | [19 empty] | Week 7 D3: Designing Role Management
[17 empty] | CODING PHASE | [14 empty] | Week 8 D1: CODING PHASE
System Dev 1 | [16 empty] | April, 2026 | [14 empty] | Week 8 D1: May, 2026
[17 empty] | Landing Page Development | [14 empty] | Week 8 D1: User Profiles
System Dev 2 | [19 empty] | April-May, 2026 | [11 empty] | Week 8 D4: May-June, 2026
|  | Indentifying System Modules | [17 empty] | Register and Login Page | [11 empty] | Week 8 D4: Accounts Management Module
System Dev 3 |  | April 1-14, 2031 | [20 empty] | May, 2026 | [8 empty] | Week 9 D3: May-June, 2026
|  | Indentifying System Modules | [20 empty] | User Registration | [8 empty] | Week 9 D3: Role based Logic Control
System Dev 4 |  | April 1-14, 2032 | [23 empty] | May. 2026 | [5 empty] | Week 10 D1: June, 2026
|  | Indentifying System Modules | [23 empty] | Admin and Veterinarian Account Creation Page | [5 empty] | Week 10 D1: Clinic Account Monitoring Module
Testing |  | April 1-14, 2033 | [27 empty] | May, 2026 |  | Week 10 D3: June, 2026
|  | Indentifying System Modules | [25 empty] | Testing |  |  |  | Week 10 D1: Testing
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ITO KASI ANG PLAN NAMIN IS A GENERALIZE LIST NG MGA IDENTIFYED MODULES